## Development
Updated on | 2009-11-24
Dev Ref | TD Ref | Task | Task description | Priority | T.E (hours) | Author | Promised for | Effort | Status | Delivered On | Accepted
DEV000001 |  | GUI doc | write the functional documentation | 1 | 4 | LCI | 2009-11-20 | 4 | Draft | 2009-11-20 |  | AAP | Adi
DEV000002 |  | Google code project | enable the Google code | 2 | 0.5 | LCI | 2009-11-20 |  | Finished | 2009-11-20 |  | LCI | Liviu
DEV000003 |  | Convertion mp3-ulow | code to import mp3 files as uLow to LifeRay | 3 | 8 | FPA |  |  | Busy | 2008-11-25 |  | FPA | Florin
DEV000004 |  | voice vs voicechat community |  | 4 |  | AAP |  |  | Busy
DEV000005 |  | GUI implementation (interface only) | Modify existing portlet to support the functionality described in document | 1 | 4 | AAP |  |  | Not Started
DEV000006 |  | Find Test tool | Find a test tool to be used for tests | 3 | 6 | LCI |  |  | Busy
DEV000007 |  | Knowledge transfer | (i.e. ramp up Florin ) | 2 | 1 | AAP, LCI |  |  | Busy
DEV000008 |  | Administrare |  | 1 | 6 | AAP,LCI
DEV000009 |  | Testare |  | 3 |  | AAP, LCI, FPA
DEV000010 |  | Project tracking |  | 1 | 3 | FPA |  |  | Busy
DEV000011 |  | SVN Code Upload |  | 1 | 1 | AAP |  | 1 | Draft
DEV000012 |  | VoiceFlow mail |  | 2 | 2 | AAP |  | 2 | Draft
DEV000013 |  | GUI Sailfin Api |  | 1 | 4 | AAP |  |  | Not Started
DEV000014 |  | Autoplay message |  | 1 | 56 | AAP |  |  | Not Started
Note on B2: Florin PADUROIU: Technical documentation ref
Note on F2: Florin PADUROIU: Time estimation
Note on G2: Florin PADUROIU: Author
Note on H2: Florin PADUROIU: Date promised
Note on I2: Florin PADUROIU: Actual effort
Note on J2: Florin PADUROIU: Actual Status
Note on K2: Florin PADUROIU: Date delivered